## Slide 1: Superior Solar Conjunction Planning
May 8, 2014
Dan Ossing
STEREO Mission Operations Manager
(240) 228-8319

## Slide 2: Agenda
HGA Feed Temperature Constraint
Schedule
Key Dates

## Slide 3: HGA Feed Temperature Constraint
HGA feed will increase in temperature beyond acceptable limits with SPE angle below 6.5 degrees.
  If SPE angle exceeded, damage to the feed assembly will render the HGA unusable.
  Thermal modeling and analysis in progress
    Results due by the end of May
    Not done before launch as the mission was only two years.
Off point HGA to prevent excessive heating
  Keep feed temperature below 125 deg C
    Temperature sensor limit = 136 deg C
    Damage starts @ 150 deg C (adhesives)
  AHEAD – September 2014 through December 2015
  BEHIND – November 2014 through January 2016
  At this time, anticipating instruments will off for these durations due to low data rates
Investigating HGA side lobe for low data rate communications
  Testing on May 10th (AHEAD) and May 17th (BEHIND)

## Slide 4: HGA Feed Assembly

## Slide 5: STEREO AHEAD Timeline Schedule - DRAFT
HGA Auto Track Low Data Rates (155 days)
HGA
Nominal
Rates
5
6
7
8
9
10
11
12
2015
2
3
4
5
6
7
8
9
10
11
12
2016
2
Reviews
FP
Readiness
MOps
Readiness
Test on S/C
Months
Solar Conjunction
Readiness
Date
SPE (deg)
9/7
6.6
9/2
6.8
3/24
2
5/20
0
7/7
2
12/15
6.8
12/9
6.6
Post Solar
Conjunction
Assessment
Activities
Load C&DH FSW 3.2.4
Load Parameters
Load MOps Macros & FP
& Set EA Bypass
Test on S/C
HGA on Side Lobe
Instrument Power Down
& SSR Reconfiguration
Rehearse w/ DSN
Solar Conjunction
No Communications
(105 days)
HGA on Main Lobe
SSR Playback &
Reconfiguration &
S/C Checkout
Instrument Power on
& Recommissioning
HGA Calibration
S/C
Config
3 axis &
Op Mode
Rotate
3 axis
& Op Mode
3 axis & Standby Mode
(198 days)
Rotate @ 5 deg/min
HCLT Reset
Every 3 days
(105 days)
3 axis &
Standby Mode
(155 days)
3 axis &
Op Mode
RF
HGA
Nominal
Rates
HGA Low
Rates
HGA Auto Track Low Data Rates (198 days)
HGA
Nominal
Rates
DSN
Nominal
Tracks
Nominal
Tracks
70m, 3 hrs
70m, Daily 3 hrs (198 days)
Nominal
Tracks
No
Coverage
(105 days)
70m, Daily
3 hrs (155 days)
Nominal
Science
Instruments
Nominal
Science
All Instr. off
Instruments Off (~469 days)
Nominal
Science
HGA Calibration
No
Communications
(105 days)

## Slide 6: STEREO BEHIND Timeline Schedule - DRAFT
HGA Auto
Track Low
Data Rates
(64 days)
Rotate @
5 deg/min
HCLT Reset
Every 3 days
(60 days)
HGA Nominal Rates
5
6
7
8
9
10
11
12
2015
2
3
4
5
6
7
8
9
10
11
12
2016
2
Reviews
FP
Readiness
MOps
Readiness
Test on S/C
Months
Solar Conjunction
Readiness
Date
SPE (deg)
11/12
7.2
11/19
6.8
1/22
2
2/19
0
3/23
2
1/12
6.8
1/18
7.2
Post Solar
Conjunction
Assessment
Activities
Load C&DH FSW 3.2.4
Load Parameters
Instrument Power Down
& SSR Reconfiguration
Rehearse w/ DSN
Solar Conjunction
No Communications
(60 days)
Instrument Power on
& Recommissioning
HGA Calibration
S/C
Config
3 axis &
Op Mode
Rotate
3 axis & Op Mode
3 axis &
Standby Mode
(295 days)
3 axis &
Op Mode
RF
HGA
Nominal
Rates
HGA Low
Rates
HGA
Nominal
Rates
DSN
Nominal Tracks
Nominal
Tracks
70m, 3 hrs
70m
Daily 3 hrs
(64 days)
Nominal
Tracks
No
Coverage
(60 days)
70m, Daily 3 hrs (295 days)
Nominal Science
Instruments
Nominal
Science
All Instr. off
Instruments Off (~432 days)
Nominal
Science
HGA Calibration
Test on S/C
SSR Playback &
Reconfiguration &
S/C Checkout
No
Comm
(60 days)
9/24
2
HGA on Main Lobe
HGA on Side Lobe
3 axis &
Standby
Mode
(64 days)
HGA Auto Track Low Data Rates (295 days)
Load MOps Macros & FP
& Set EA Bypass

## Slide 7: Key Dates
Event | AHEAD | BEHIND
HGA side lobe test | 5/10/14 | 5/17/14
LGA calibration test | 6/8/14 | 5/23/14
Load C&DH 3.2.4 FSW to EEPROM Copy 1 | 5/20/14 | 5/20/14
Load G&C and C&DH parameters to EEPROM | 5/28/14 | 5/28/14
Load MOps macros & FP releases to EEPROM | 6/10/14 | 6/10/14
MOps Readiness for S/C Testing Review | 6/19/14 | 9/18/14
S/C Testing – Instruments off/on | 7/7 thru 7/15/14 | 9/29 thru 10/6/14
HGA Calibration – Pre-conjunction | 7/23/14 | 7/23/14
Load C&DH 3.2.4 FSW to EEPROM Copy 2 | 7/28/14 | 7/28/14
Solar Conjunction Readiness Review | 8/14/14 | 10/23/14
Instrument Power Down & SSR Reconfiguration | 9/2/14 | 11/14/14
Rehearse with DSN | 9/5/14 | 11/16/14
HGA on Side Lobe | 9/7/14 | 11/19/14
Superior Solar Conjunction | 3/24 thru 7/7/15 | 1/22 thru 3/23/15
HGA on Main Lobe | 12/9/15 | 1/12/16
SSR Playback & Reconfiguration & S/C Checkout | 12/10/15 | 1/13/16
Instrument Power on & Recommissioning | 12/15/15 | 1/18/16
HGA Calibration – Post-conjunction | 1/27/16 | 1/27/16
Post Solar Conjunction Assessment Review | 3/16 | 3/16

## Slide 9: Three Laws of STEREO Solar Conjunction
Take all reasonable precautions to keep the observatory safe.
  Of course, “reasonable” is subject to interpretation and judgment. We will be guided by the usual risk assessment methodology of weighing both probability and impact, which is, after all, the implicit thinking behind “engineering judgment.”
Return to normal science operations as soon as reasonably possible. In cases where this law conflicts with the First Law, the First Law takes precedence.
  There’s that word “reasonably” again. We do not have infinite time and manpower to prepare for conjunction. So, some management judgment is required.
Conduct science operations during conjunction, if reasonably feasible. In cases where this law conflicts with the first two, the first two laws take precedence.
  We do not have infinite time and manpower.